## Task
ID | Name | Task | Responsible | Days to Complete | Relevant Requirements | Dependencies | Notes | Completed? | Date Completed | extra notes lol
ANALYSIS-0100 Engine Characterisation
ANALYSIS-0110 | Ablation Rates | Characterise the instantaneous ablation rate at nozzle end |  | 21 |  |  |  | No
ANALYSIS-0111 | Expansion Ratio | Log Expansion Ratio Vs Time |  | 14 |  | ANALYSIS-0110 |  | No
ANALYSIS-0112 | Throat Ablation | Model throat ablation rate. |  | 14 |  | ANALYSIS-0110 | Map nozzle ablation to throat, scaled for throat dA | No
ANALYSIS-0120 | Exhaust Pressures | Characterise the exhaust exit pressure |  | 21 |  |  |  | No
ANALYSIS-0121 | Pe Equations | Determine Equation to estimate Pe with known variables |  | 14 |  |  |  | No
ANALYSIS-0122 | Pe Change | Investigate if Pe changes throughout Burntime |  | 14 |  | ANALYSIS-0121 |  | No
ANALYSIS-0130 | Convective Heat Transfer Coefficient | Characterise the convective heat transfer coefficient |  | 21 |  |  |  | No
ANALYSIS-0131 | Coefficient at Throat | Find heat transfer coeffecient between exhaust gasses and wall at throat |  | 14 |  |  |  | No
ANALYSIS-0132 | Coefficient in Expansion Nozzle | [6 empty] | No
ANALYSIS-0140 | Chamber Pressures | Estimate chamber pressure from exhaust pressure |  | 12 |  | ANALYSIS-0120 |  | No
ANALYSIS-0141 | Pc Equations | Determine Equation to estimate Pc with known variables |  | 14 |  |  |  | No
ANALYSIS-0142 | Pc Change | Investigate if Pc changes throughout Burntime |  | 14 |  | ANALYSIS-0120 |  | No
ANALYSIS-0150 | Pressure Characterisation | Log propellant pressures and mass flow rates |  | 20 |  |  |  | No
ANALYSIS-0151 | Nox Pt vs mdot | Determine response between Nox tank pressure and mdot |  | 14 |  |  |  | No
ANALYSIS-0152 | Nox Pi vs mdot | Determine response between Nox inlet pressure and mdot |  | 14 |  |  |  | No
ANALYSIS-0153 | IPA Pt vs mdot | Determine response between IPA tank pressure and mdot |  | 14 |  |  |  | No
ANALYSIS-0154 | IPA Pi vs mdot | Determine response between Nox IPA pressure and mdot |  | 14 |  |  |  | No
ANALYSIS-0160 | Thrust Characterisation | Log any corollations between thrust and other measured characteristics |  | 28 |  | ANALYSIS-0110 to 0140 |  | No |  | I want to know why thurst is constant eventhough massflow increases with time. If you can find an explanation for this,
ANALYSIS-0161 | ER Vs Pe 1 | Determine theoretical relation between Exit pressure to Exp. Ratio Change. |  | 14 |  | ANALYSIS-0111 |  | No
ANALYSIS-0162 | ER Vs Pe 2 | Determine actual response of Chamber pressure to Exp. Ratio Change. |  | 14 |  | ANALYSIS-0111 |  | No
ANALYSIS-0163 | mdot Vs t Throat | Knowing throat is choked, calc theoretical mdot vs time with throat ablation. |  | 14 |  | ANALYSIS-0112 | Does mdot data correspond? You will need to assume constant chamber temp, calculate throat temp | No |  | Mdot throat from wiki
ANALYSIS-0164 | mdot Vs t Throat | Knowing throat is chocked, calc throat temp using mdot data from fire |  | 14 |  | ANALYSIS-0112 | Like previous task, only using mdot values and letting throat temperature change | No |  | This could be pausible if chamber ablation rates increase with time, increasing cooling within combustion chamber
ANALYSIS-0165 | Anything | Any insightful findings on engine variable relations highly welcomed |  | N/A |  |  |  | No
MCOR-PERF-0100 Ignition system
MCOR-PERF-0110 | Igniter Design | Design Igniter Interface |  | 14 |  |  |  | No
MCOR-PERF-0111 | Igniter Design | Design Solid-Rocket Igniter |  | 14 |  |  |  | No
MCOR-PERF-0111 | Igniter Design | Design Spark Igniter |  | 14 |  |  |  | No
MCOR-PERF-0120 | Igniter Build | Build Igniter |  | 28 |  | MCOR-PERF-011X |  | No
MCOR-PERF-0130 | Igniter Test | Test design(s) -5 concurrent successful tests |  | 18 |  | MCOR-PERF-011X to 012X |  | No
MCOR-PERF-0131 | Igniter Test | Physics of Failure (PoF) analysis |  | 21 |  | MCOR-PERF-011X to 012X |  | No
DESIGN-0100 Engine Design
DESIGN-0120 | Injector | Weight saving on injector |  | 21 |  |  |  | No
DESIGN-0130 | Shell | Redsign Shell to be lighter and cheaper to manufacture |  | 28 |  |  |  | No
DESIGN-0140 | Graphite Insert | Redsign Graphite insert to be smaller and seamless intergration |  | 14 |  |  |  | No
DESIGN-0150 | Interface | Design Interface with Fuel Systems |  | 21 |  | Fuel Systems |  | No
DESIGN-0160 | Chamber/Nozzle | Adapt Chamber to be vacuum infused |  | 60 |  |  |  | No
DESIGN-0170 | Regenerative Throat Insert | Design (cheaply) manufacturable geometry for regenerative insert |  | 60 |  | Fuel Systems |  | No
VOR-TEST-0210 | Pressure Sensor | Engine Chamber design updated to fit pressure sensor |  | 21 |  | Avionics |  | No
BUILD-0100 Engine Build | [7 empty] | No
BUILD-0110 | Injector | Build Injector |  | 45 |  |  |  | No
BUILD-0120 | Shell | Build Shell |  | 45 |  |  |  | No
BUILD-0130 | Graphite Insert | Build Graphite Insert |  | 30 |  |  |  | No
BUILD-0140 | Interface | Build Interface with Fuel Systems |  | 28 |  | Fuel Systems |  | No
BUILD-0150 | Chamber/Nozzle | Build Chamber and Nozzle |  | 60 |  |  |  | No
BUILD-0160 | Regenerative Throat Insert | Build regenerative throat insert |  | 45 |  |  |  | No
BUILD-0100 Engine Test
VOR-TEST-0310 | Engine Prep 02 | Pressure test engine and chamber to a factor of 1.5x expected pressures for twice the operating time. |  | 1 |  |  |  | No
VOR-PERF-0100 Sims
VOR-PERF-0110 | Sims 01 | Improve ideal conditions sim to beter reflect launch conditions. Additions to be made include: Launch angle considerations, humidity factor, elavation considerations, wind data? |  | 42 |  | Vehicle Structures |  | No
VOR-PERF-0120 | Sims 02 | Regularly update sim to ensure launch rail exit velocity exeeds 30 m/s, come up with adequate safety factor |  | 7 |  |  |  | No
VOR-PERF-0130 | Sims 03 | Implement engine thrust curve into sim |  | 14 |  |  |  | No
VOR-PERF-0140 | Feedback | Work with avionics team to log vehicle altitude, velocity, tank pressures and acceleration throughout launch. This data can be used to validate reflect and improve on the launch sims |  | 42 |  | Avionics, Vehicle structures, Fuel System |  | No

## Back End
Yes
No